## Overview
Bailey & Beau — QA Test Plan
Interactive Family Reading & Activity Platform · MVP Beta QA · Version 1.0
Project | Bailey & Beau MVP
QA Phase | Pre-Beta + Beta
Tech Stack | Next.js · Django + DRF · Livekit · PostgreSQL · Stripe · S3
Target Browsers | iOS Safari · Android Chrome · macOS Chrome/Safari · Windows Chrome/Edge
Owner | QA Lead
Last Updated | 28 March 2026
How to use this workbook
1. QA Lead assigns each test case to a tester (column "Assigned Tester").
2. Tester executes the steps, sets Status = Pass / Fail / Blocked, and logs the date in "Tested On".
3. If Fail, log a bug in the "Bug Log" sheet and reference the Bug ID back in the test case row.
4. Use "Cross-Browser Matrix" to track compatibility across all required browsers / devices.
5. Critical and High tests must be 100% Pass before beta launch sign-off.
6. Re-run regression suite (all Critical + High) after each significant code change.
Sheet index
Frontend QA | UI test cases — Reading Room, Activity Room, Lobby, Customer Dashboard, Admin UI, Auth/Invite flow
Backend QA | API, database, JWT auth, Livekit token, Stripe webhooks, S3 storage, badge signals
Integration QA | End-to-end flows, real-time sync, auto-reconnection, host delegation, billing-to-quota
Non-Functional QA | Performance, security, accessibility, reliability, compliance (GDPR)
Cross-Browser Matrix | Per-browser/device pass-fail tracking for the smoke suite
Bug Log | Defect tracking — ID, severity, status, owner, linked test case
Priority Legend | Definitions for Critical / High / Medium / Low and Test Types

## Frontend QA
Frontend QA — Test Cases
Status values: Not Started · In Progress · Pass · Fail · Blocked · Deferred
Test ID | Module | Feature | Test Scenario | Pre-conditions | Test Steps | Expected Result | Priority | Test Type | Status | Assigned Tester | Tested On | Browser / Device | Bug ID | Notes
FE-RR-001 | Reading Room | Session Entry | Verify reading room loads after joining via valid invite link | Valid session link generated; both participants on supported browsers | 1. Host opens session URL 2. Participant opens same URL on different device 3. Both grant camera/mic permission 4. Both click Ready | Reading Room renders with book viewer, video tiles, annotation toolbar, timer; both video streams visible | Critical | Smoke
FE-RR-002 | Reading Room | Video Stream | Verify both participants see each other's video | Session established; both cameras enabled | 1. Confirm self-view tile renders 2. Confirm remote tile renders 3. Wave hand and confirm motion shows on remote screen | Both video streams show within 3s; no black tiles; no severe lag (<150ms perceived) | Critical | Functional
FE-RR-003 | Reading Room | Audio | Verify two-way audio works clearly | Mics enabled; speakers/headphones working | 1. Host speaks 2. Confirm participant hears 3. Participant speaks 4. Confirm host hears | Audio is clear, no echo, no significant lag | Critical | Functional
FE-RR-004 | Reading Room | Camera Toggle | Verify camera can be toggled off and on | Camera enabled at session start | 1. Click camera-off button 2. Verify own tile shows avatar/placeholder on remote view 3. Click camera-on 4. Verify video resumes | Camera toggles cleanly; remote view updates within 1s; no session crash | High | Functional
FE-RR-005 | Reading Room | Mic Mute | Verify mic can be muted and unmuted | Mic enabled at session start | 1. Click mute 2. Speak — confirm remote hears nothing 3. Click unmute 4. Speak — confirm remote hears | Mute icon shows on muted tile; audio cuts cleanly; unmute restores audio | High | Functional
FE-RR-006 | Reading Room | Book Viewer | Verify book pages render at correct aspect ratio | Book uploaded and published in admin | 1. Enter session linked to a book 2. Inspect first page render | Page renders crisp, correct aspect ratio, fits viewport without horizontal scroll | Critical | UI
FE-RR-007 | Reading Room | Page Turn — Host | Verify host can navigate forward and backward | Host role assigned | 1. Host clicks Next 2. Confirm page increments 3. Host clicks Previous 4. Confirm page decrements | Page index changes correctly; current page is highlighted; no flicker | Critical | Functional
FE-RR-008 | Reading Room | Page Sync | Verify participant view updates within 200ms of host page turn | Both participants in session | 1. Host clicks Next 2. Time gap until participant view updates 3. Repeat 5 times across session | Average sync latency under 200ms; never exceeds 500ms | Critical | Performance
FE-RR-009 | Reading Room | Page Turn — Participant Lockout | Verify participant cannot turn pages | Participant role assigned | 1. Participant inspects toolbar 2. Attempt keyboard arrow shortcuts | Page navigation controls are not visible/active for participant; arrow keys do nothing | Critical | Security
FE-RR-010 | Reading Room | Host Indicator | Verify host badge is visible to both users | Host role assigned | 1. Both join session 2. Inspect each tile / username area | Host tile shows a clear "Host" badge; participant tile does not | Medium | UI
FE-RR-011 | Reading Room | Annotation — Pen | Verify pen tool draws on book page | Session active; pen tool selected | 1. Select pen 2. Draw a line on the page 3. Verify stroke appears on own canvas | Stroke appears immediately, smooth, follows pointer accurately | Critical | Functional
FE-RR-012 | Reading Room | Annotation — Sync | Verify drawings appear on remote screen within 200ms | Both users in session, pen selected | 1. Host draws a circle 2. Time delta until remote sees full stroke 3. Participant draws a square 4. Verify host sees it | Sync latency under 200ms; strokes render in correct position; no missing segments | Critical | Performance
FE-RR-013 | Reading Room | Annotation — Eraser | Verify eraser removes strokes | Pen marks already on canvas | 1. Switch to eraser 2. Drag across existing strokes 3. Verify removal locally and on remote | Erased strokes disappear on both screens; no orphan fragments | High | Functional
FE-RR-014 | Reading Room | Annotation — Color Picker | Verify color picker changes pen color | Pen tool selected | 1. Open color picker 2. Select 3 different colors 3. Draw with each 4. Verify on remote | Each stroke renders in selected color on both screens | Medium | Functional
FE-RR-015 | Reading Room | Annotation — Clear on Page Turn | Verify canvas clears when host turns page | Drawings exist on current page | 1. Draw several strokes 2. Host turns page 3. Inspect new page canvas | Canvas is clean on new page; previous strokes do not bleed through | High | Functional
FE-RR-016 | Reading Room | Session Timer | Verify 20-minute countdown is visible to both users | Session started | 1. Both inspect timer area 2. Compare timer values across screens | Timer visible on both screens; values within 1s of each other | Critical | Functional
FE-RR-017 | Reading Room | Timer — 5-min Warning | Verify 5-min warning notification appears | Session running | 1. Wait until timer reaches 05:00 2. Observe both screens | Visible warning toast/banner appears on both screens; non-blocking; dismissable | High | Functional
FE-RR-018 | Reading Room | Timer — 2-min Warning | Verify 2-min warning notification appears | Session running | 1. Wait until timer reaches 02:00 2. Observe both screens | Visible final warning appears on both screens | High | Functional
FE-RR-019 | Reading Room | Timer — Session End | Verify session ends gracefully at 0:00 | Session running, timer near zero | 1. Allow timer to reach 0:00 2. Observe behaviour on both screens | Session closes cleanly; users routed to wrap-up / badge screen; no error | Critical | Functional
FE-AR-001 | Activity Room | Drawing Activity | Verify drawing activity loads with configured outlines | Activity config with drawing type linked to book | 1. Enter activity room 2. Select drawing activity 3. Inspect colouring outline | Outline image renders; brush, palette, eraser visible; matches admin config | Critical | Functional
FE-AR-002 | Activity Room | Drawing — Brush Size | Verify brush size control works | Drawing activity active | 1. Change brush size to small 2. Draw 3. Change to large 4. Draw | Stroke width changes accordingly; both sizes sync to remote | Medium | Functional
FE-AR-003 | Activity Room | Drag-and-Drop — Drag | Verify draggable items can be dragged | Drag-and-drop activity loaded | 1. Click and hold draggable item 2. Move pointer 3. Verify item follows | Item moves smoothly with pointer; remote sees movement in real-time | Critical | Functional
FE-AR-004 | Activity Room | Drag-and-Drop — Correct Drop | Verify correct drop shows positive feedback | Drag-and-drop active; correct zone defined | 1. Drag item to correct zone 2. Release | Visual success feedback (color, animation, sound if configured); item locked in place | Critical | Functional
FE-AR-005 | Activity Room | Drag-and-Drop — Incorrect Drop | Verify incorrect drop shows negative feedback and resets | Drag-and-drop active | 1. Drag item to wrong zone 2. Release | Visual error feedback; item snaps back to origin | High | Functional
FE-AR-006 | Activity Room | Quiz — Render | Verify quiz renders question and up to 4 options | Quiz config saved with 4 options | 1. Load quiz activity 2. Inspect question and options | Question text and all configured options visible on both screens | Critical | Functional
FE-AR-007 | Activity Room | Quiz — Reveal Answer | Verify host can reveal correct answer | Quiz active; participant has selected an answer | 1. Host clicks Reveal 2. Observe both screens | Correct answer highlighted; result shown to both users | High | Functional
FE-AR-008 | Activity Room | Hotspot — Mouse | Verify hotspot zones respond to mouse click | Hotspot activity active on desktop | 1. Hover defined hotspot zone 2. Click | Cursor changes to pointer; click triggers configured tooltip/popup | High | Functional
FE-AR-009 | Activity Room | Hotspot — Touch | Verify hotspot zones respond to touch tap | Hotspot activity active on iPad/iPhone/Android tablet | 1. Tap each defined hotspot 2. Confirm tooltip/popup | Touch tap triggers tooltip/popup as configured | High | Functional
FE-AR-010 | Activity Room | Activity — Host Progress Control | Verify only host can advance or reset activity | Activity active | 1. Host clicks Next/Reset 2. Participant inspects controls | Host controls work; participant has no Next/Reset buttons | Critical | Security
FE-AR-011 | Activity Room | Activity — Sync Latency | Verify all activity interactions sync within 200ms | Activity active, two users | 1. Perform 10 rapid interactions (drag/click/draw) 2. Measure remote update latency | Average sync under 200ms; no dropped events | Critical | Performance
FE-LB-001 | Pre-Session Lobby | Lobby Render | Verify lobby renders for first joiner | Valid invite link | 1. First user opens link 2. Observe screen | Lobby with camera preview, mic level, book preview, Ready button visible | Critical | Smoke
FE-LB-002 | Pre-Session Lobby | Camera Permission | Verify camera permission requested | First time on browser | 1. Open lobby 2. Observe browser prompt | Browser camera permission prompt appears; on grant, preview starts | Critical | Functional
FE-LB-003 | Pre-Session Lobby | Mic Permission | Verify mic permission requested | First time on browser | 1. Open lobby 2. Observe browser prompt | Browser mic permission prompt appears; on grant, mic level meter activates | Critical | Functional
FE-LB-004 | Pre-Session Lobby | Camera Preview | Verify own camera preview shows in lobby | Camera permission granted | 1. Inspect camera preview tile | Self-view renders within 2s; correct aspect ratio | High | UI
FE-LB-005 | Pre-Session Lobby | Book Preview | Verify book title and estimated duration shown | Session linked to a book | 1. Open lobby 2. Inspect book preview area | Title and "20 minutes" duration visible | Medium | UI
FE-LB-006 | Pre-Session Lobby | Ready Confirmation | Verify both Ready clicks required to start | Both users in lobby | 1. User A clicks Ready 2. Confirm session does not start 3. User B clicks Ready 4. Observe | Session starts only after both Ready; pre-session state is clearly indicated | Critical | Functional
FE-CD-001 | Customer Dashboard | Login | Verify dashboard accessible after login | Valid customer account | 1. Log in 2. Land on dashboard | Dashboard renders without error; navigation visible | Critical | Smoke
FE-CD-002 | Customer Dashboard | Active Plan | Verify current subscription plan displayed | User has active Stripe subscription | 1. Open dashboard 2. Inspect plan section | Plan name, price, renewal date displayed correctly | High | Functional
FE-CD-003 | Customer Dashboard | Session Quota | Verify remaining session count displayed | User has remaining sessions | 1. Open dashboard 2. Note quota 3. Complete a session 4. Reload | Quota decrements by 1 after completed session | Critical | Functional
FE-CD-004 | Customer Dashboard | Billing History | Verify past invoices visible | User has billing history in Stripe | 1. Navigate to Billing 2. Inspect list | All past invoices listed with date, amount, status | Medium | Functional
FE-CD-005 | Customer Dashboard | Badge — Display | Verify earned badges shown on profile | User has at least one badge | 1. Open profile/dashboard 2. Inspect badges section | All earned badges render with correct artwork and label | High | UI
FE-CD-006 | Customer Dashboard | Badge — Reveal Animation | Verify animated reveal on new badge | User just completed a session that awards a badge | 1. Complete session 2. Observe end-of-session screen 3. Land on dashboard | Animated badge reveal plays once; badge persists in collection | Medium | UI
FE-AD-001 | Admin Portal | Admin Login | Verify admin can log in via Django admin | Superuser account exists | 1. Visit /admin 2. Enter credentials | Admin dashboard loads; menu items visible | Critical | Smoke
FE-AD-002 | Admin Portal | Book Upload | Verify book PDF upload works through admin | Admin logged in | 1. Books > Add 2. Fill title, room type, age range 3. Upload PDF 4. Save | Book saved; appears in book list; PDF accessible in S3 | Critical | Functional
FE-AD-003 | Admin Portal | Book Image Set Upload | Verify book image-set upload works | Admin logged in | 1. Books > Add 2. Upload image sequence 3. Save | All images uploaded to S3; correct ordering preserved | High | Functional
FE-AD-004 | Admin Portal | Book Filters | Verify books can be filtered by type, age range, status | Multiple books exist | 1. Open Books list 2. Apply each filter independently | Filtered list returns only matching records | Medium | Functional
FE-AD-005 | Admin Portal | Activity Config Form | Verify activity config form renders for each type | Admin logged in | 1. ActivityConfigs > Add 2. Select each of 4 types | Form fields update appropriately for each activity type | Critical | Functional
FE-AD-006 | Admin Portal | Activity Config — JSON Validation | Verify invalid JSON is rejected on save | Admin logged in | 1. Add Activity Config 2. Enter malformed JSON 3. Save | Validation error shown; record not saved | High | Validation
FE-AD-007 | Admin Portal | Session Monitoring View | Verify session list view loads | Several sessions exist | 1. Navigate to Sessions in admin | List shows session ID, participants, start time, duration, status | High | Functional
FE-AD-008 | Admin Portal | Session — CSV Export | Verify session log export to CSV works | Sessions exist | 1. Open Sessions list 2. Click Export CSV | CSV downloads with all expected columns and rows | Medium | Functional
FE-AD-009 | Admin Portal | Subscription View | Verify subscription overview loads | Stripe subscriptions exist | 1. Navigate to Subscriptions admin view | Active, past-due, cancelled subs visible with customer info | Medium | Functional
FE-AD-010 | Admin Portal | Badge Config | Verify badge types and trigger conditions configurable | Admin logged in | 1. Open Badges admin 2. Add new badge with trigger | Badge saved; visible in list; will be awarded on matching trigger | High | Functional
FE-AU-001 | Auth & Invite | Invite Link Generation | Verify customer can generate invite link | Customer logged in with available session | 1. Click "Start Session" / "Invite" 2. Inspect generated link | Unique session URL generated; copyable; share button works | Critical | Functional
FE-AU-002 | Auth & Invite | Join — No Account | Verify invited user can join without creating account | Valid invite link | 1. Open link in incognito browser 2. Follow flow to lobby | User reaches lobby in 3 clicks or fewer; no signup wall | Critical | Functional
FE-AU-003 | Auth & Invite | Host Delegation Indicator | Verify when invitee is granted host, host UI is shown to them | Inviter created link with host_role = invitee | 1. Inviter generates host-delegated link 2. Invitee opens and joins | Invitee enters session as host with full controls; host badge on their tile | Critical | Functional
FE-AU-004 | Auth & Invite | Expired Link | Verify expired invite link shows clear error | Generate link, wait past expiry (or simulate) | 1. Open expired link 2. Observe screen | Friendly error message shown; option to request a new link | High | Validation
FE-AU-005 | Auth & Invite | Single-Use Link Reuse | Verify single-use link cannot be reused (if config = single-use) | Single-use link consumed once | 1. Open consumed link in new browser | Error: link already used; no session entry granted | High | Security

## Backend QA
Backend QA — Test Cases
Status values: Not Started · In Progress · Pass · Fail · Blocked · Deferred
Test ID | Module | Feature | Test Scenario | Pre-conditions | Test Steps | Expected Result | Priority | Test Type | Status | Assigned Tester | Tested On | Browser / Device | Bug ID | Notes
BE-AU-001 | Authentication | JWT Issuance | Verify JWT issued on valid login | Valid user credentials | 1. POST /api/auth/login with valid creds 2. Inspect response | 200 OK; access + refresh tokens returned; correct claims (user_id, role, exp) | Critical | API
BE-AU-002 | Authentication | JWT Validation | Verify protected endpoints reject missing/invalid tokens | Protected endpoint exists | 1. Call protected endpoint without token 2. Call with malformed token 3. Call with expired token | All return 401 with appropriate error code | Critical | Security
BE-AU-003 | Authentication | Refresh Token | Verify refresh token issues new access token | Valid refresh token | 1. POST /api/auth/refresh with refresh token | New access token returned with extended expiry | High | API
BE-AU-004 | Authentication | Role-Based Access | Verify non-admin cannot access admin endpoints | Standard user JWT | 1. Call admin-only endpoint with user JWT | 403 Forbidden returned | Critical | Security
BE-AU-005 | Authentication | Token Expiry | Verify expired token rejected | Token past exp | 1. Call protected endpoint with expired token | 401 returned with token_expired error code | High | Security
BE-SE-001 | Session API | Create Session | Verify POST /api/sessions creates valid session | Authenticated customer with available quota | 1. POST /api/sessions with book_id 2. Inspect response | 201 Created; session_id, invite_url, livekit_token returned; DB row exists | Critical | API
BE-SE-002 | Session API | Quota Enforcement | Verify session creation fails when quota exhausted | User has 0 sessions remaining | 1. POST /api/sessions | 402/403 returned with quota_exhausted error | Critical | API
BE-SE-003 | Session API | Get Session | Verify GET /api/sessions/:id returns session detail | Existing session | 1. GET /api/sessions/{id} | 200 OK; full session data including book, host_id, status | High | API
BE-SE-004 | Session API | Invalid Session ID | Verify invalid session ID returns 404 |  | 1. GET /api/sessions/invalid-uuid | 404 Not Found | Medium | API
BE-SE-005 | Session API | Host Role Persistence | Verify host role flag stored correctly | Session created with delegated host | 1. Create session with host_role = invitee 2. Inspect DB | host_role correctly written; visible in admin and API response | Critical | Data
BE-SE-006 | Session API | Session Expiry | Verify session token expiry is enforced | Session past expiry | 1. Attempt to join expired session | Reject with session_expired | High | Security
BE-SE-007 | Session Logging | Start Event | Verify session_started signal fires on first join | New session, first join | 1. Trigger first join 2. Inspect Django signals + DB log | session_started log entry written with timestamp | High | Audit
BE-SE-008 | Session Logging | End Event | Verify session_ended signal fires on completion | Session reached 0:00 or both users left | 1. Complete session 2. Inspect logs | session_ended entry written with duration | High | Audit
BE-SE-009 | Session Logging | Reconnection Event | Verify reconnection event logged | Active session; participant drops and reconnects | 1. Force disconnect 2. Reconnect 3. Inspect logs | reconnection log entry written with user and timestamp | Medium | Audit
BE-LK-001 | Livekit | Token Generation | Verify Livekit token issued for valid session | Authenticated user, valid session | 1. Call token endpoint | Token returned; decodable; identity, room, grants correct | Critical | Integration
BE-LK-002 | Livekit | Host Grants | Verify host token has different grants than participant | Session with both roles | 1. Inspect host token grants 2. Inspect participant token grants | Host has additional permissions (e.g. can_publish_data, room admin where applicable) | High | Security
BE-LK-003 | Livekit | Token Expiry | Verify token expiry matches session window | New session token | 1. Decode token, inspect exp claim | exp = session start + 30 min (or configured value); matches policy | High | Security
BE-LK-004 | Livekit | Token Reuse Across Reconnect | Verify same token works for reconnection within session | Session active; user disconnects | 1. User reconnects with same token within session window | Reconnection succeeds; no new token required | High | Functional
BE-CR-001 | Book CRUD | Create Book | Verify book record created with all fields | Admin authenticated | 1. Create book via admin or API 2. Inspect DB | All fields persisted: title, room_type, age_range, status, file_path | Critical | Data
BE-CR-002 | Book CRUD | S3 Upload | Verify book asset uploaded to S3 | PDF or image set provided | 1. Upload via admin 2. Verify file in S3 bucket | File present in S3; signed URL retrievable; CDN cache works | Critical | Storage
BE-CR-003 | Book CRUD | Signed URL | Verify GET on book returns signed S3 URL | Book exists with asset | 1. GET /api/books/{id} | Response includes valid signed URL with expiry | High | Security
BE-CR-004 | Activity Config | Validation | Verify activity config JSON validated on save | Admin authenticated | 1. Save activity with malformed/invalid JSON | Save fails; validation error returned | High | Validation
BE-CR-005 | Activity Config | Linked to Book | Verify activity config foreign key to Book | Activity created | 1. Inspect DB row | book_id FK populated; cascade rules behave as designed | High | Data
BE-CR-006 | Activity Config | Reuse Across Books | Verify a single activity config can be linked to multiple books |  | 1. Assign activity_config_id to two book records 2. Load activity in each session | Both sessions render activity correctly using same config | Medium | Functional
BE-CR-007 | Book CRUD | Published Filter | Verify only published books surface in customer-facing API | Mix of published and draft books | 1. Call public book list endpoint | Only is_published=True books returned | High | API
BE-ST-001 | Stripe | Checkout Session | Verify Stripe checkout session can be created | User logged in; plan exists | 1. POST /api/billing/checkout with plan_id 2. Inspect response | Stripe checkout URL returned; valid session ID | Critical | Integration
BE-ST-002 | Stripe | Webhook — subscription.created | Verify subscription.created webhook updates user record | Webhook endpoint configured | 1. Trigger test event from Stripe CLI 2. Inspect DB | User subscription record created; status=active; quota set | Critical | Integration
BE-ST-003 | Stripe | Webhook — invoice.paid | Verify invoice.paid webhook increments quota / extends sub | Active subscriber | 1. Trigger invoice.paid via Stripe CLI 2. Inspect quota | Quota refreshed; renewal_date updated | Critical | Integration
BE-ST-004 | Stripe | Webhook — payment_failed | Verify failed payment marks sub past_due | Active subscriber, simulated failure | 1. Trigger invoice.payment_failed 2. Inspect DB and customer dashboard | Subscription status flipped to past_due; user notified | High | Integration
BE-ST-005 | Stripe | Webhook — subscription.deleted | Verify cancellation revokes future quota | Active subscriber cancels | 1. Trigger subscription.deleted 2. Inspect DB | Subscription marked cancelled; remaining sessions handled per policy | High | Integration
BE-ST-006 | Stripe | Session Pack Purchase | Verify one-off pack purchase increments session count | Logged-in user | 1. Complete pack checkout 2. Webhook fires 3. Inspect quota | Quota increased by pack size; transaction logged | High | Integration
BE-ST-007 | Stripe | Webhook Signature | Verify webhooks reject invalid signature |  | 1. POST to webhook endpoint without/with bad signature | 400 returned; event ignored | Critical | Security
BE-ST-008 | Stripe | Webhook Idempotency | Verify duplicate webhook events not double-processed | Test mode | 1. Replay same event twice 2. Inspect quota | Quota incremented only once; idempotency key respected | High | Integration
BE-BD-001 | Badges | Award on Session Complete | Verify badge awarded on session_completed signal | Configured badge with completion trigger; user has not yet earned it | 1. Complete a session 2. Inspect Badge table | Badge row inserted for user with correct type and timestamp | High | Functional
BE-BD-002 | Badges | Idempotency | Verify duplicate badge not awarded | User already has a one-time badge | 1. Trigger same condition again 2. Inspect badges | No duplicate row; or counter incremented per design | High | Data
BE-BD-003 | Badges | Admin Editable | Verify badges can be edited via Django admin | Admin logged in | 1. Edit badge name/icon/trigger 2. Save | Updated values persist; affect future awards | Medium | Functional
BE-DB-001 | Database | Migrations | Verify all migrations apply cleanly on fresh DB | Empty Postgres DB | 1. Run python manage.py migrate | All migrations apply with no errors; tables created | Critical | Smoke
BE-DB-002 | Database | FK Constraints | Verify FK constraints prevent orphan rows | Existing data | 1. Attempt to delete a Book with linked sessions 2. Observe | Either cascades correctly or blocks per design; no orphan rows | High | Data
BE-DB-003 | Database | JSON Field Validation | Verify ActivityConfig JSON fields enforce schema |  | 1. Insert invalid JSON via shell | Validation error raised on .full_clean() | High | Data
BE-DB-004 | Database | Indexes | Verify required indexes exist (session_id, user_id, etc.) |  | 1. Inspect Postgres indexes | Indexes present on high-cardinality lookup columns | Medium | Performance

## Integration QA
Integration QA — Test Cases
Status values: Not Started · In Progress · Pass · Fail · Blocked · Deferred
Test ID | Module | Feature | Test Scenario | Pre-conditions | Test Steps | Expected Result | Priority | Test Type | Status | Assigned Tester | Tested On | Browser / Device | Bug ID | Notes
INT-E2E-001 | End-to-End | Happy Path — Full Session | Parent invites grandparent, full 20-min reading session, badge awarded | Account, book, activity config in place | 1. Parent logs in 2. Generates invite 3. Grandparent joins 4. Both ready 5. 20-min session 6. Session ends 7. Badge awarded | Session completes end-to-end; badge appears on dashboard; logs written | Critical | E2E
INT-E2E-002 | End-to-End | Happy Path — Activity Session | Full session including 2+ activities | Activity-room book + configs | 1. Start activity-room session 2. Run drawing 3. Run drag-drop 4. Run quiz 5. Run hotspot 6. End session | All activities load and complete; sync stable; no errors | Critical | E2E
INT-HD-001 | Host Delegation | Parent Delegates to Grandparent | Inviter grants host role to invitee | Customer logged in | 1. Generate invite with host_role=invitee 2. Grandparent joins 3. Verify host controls available to grandparent | Grandparent has full host UI; parent has participant UI | Critical | Functional
INT-HD-002 | Host Delegation | Mid-Session Host Transfer | Original inviter transfers host role mid-session | Active session | 1. Inviter clicks Transfer Host 2. Confirm 3. Verify both UIs flip | Host role moves; controls swap immediately on both clients | Medium | Functional
INT-RC-001 | Reconnection | Auto-reconnect <10s | Drop participant connection and verify auto-rejoin | Active session | 1. Disable network on participant device 2. Wait 5s 3. Re-enable 4. Time until reconnected | Reconnection completes in <10s; "Reconnecting..." status visible during | Critical | Reliability
INT-RC-002 | Reconnection | Page State Preserved | Verify current page is preserved after reconnect | Session on page 5 | 1. Drop connection 2. Reconnect 3. Inspect page | Reconnected client lands on page 5 | Critical | Reliability
INT-RC-003 | Reconnection | Canvas State Preserved | Verify drawings on current page survive reconnect | Drawings exist on current page | 1. Drop connection 2. Reconnect | Reconnected client sees same canvas content | High | Reliability
INT-RC-004 | Reconnection | Timer State Preserved | Verify timer continues from correct value after reconnect | Timer at 12:34 | 1. Drop 2. Reconnect within 10s | Timer resumes from ~current value, not reset | High | Reliability
INT-RT-001 | Real-Time Sync | Page Turn Latency | Measure page turn sync latency over 20 turns | Active session | 1. Host turns page 20 times 2. Measure each delta | Average <200ms; max <500ms; no missed turns | Critical | Performance
INT-RT-002 | Real-Time Sync | Drawing Sync Latency | Measure annotation sync over 30s of continuous drawing | Active session | 1. Draw continuously for 30s 2. Measure remote render lag | Average <200ms; no dropped strokes; smooth render on remote | Critical | Performance
INT-RT-003 | Real-Time Sync | Activity Sync Latency | Measure drag-drop sync | Drag-drop active | 1. Drag 10 items 2. Measure remote update lag | Average <200ms; correct snap-to-zone state on remote | Critical | Performance
INT-SUB-001 | Subscription Flow | Signup to First Session | New user signs up, subscribes, runs first session, badge awarded | Stripe in test mode | 1. Sign up 2. Subscribe to plan 3. Webhook completes 4. Generate invite 5. Run session 6. Badge issued | End-to-end flow works; quota correctly debited; badge appears | Critical | E2E
INT-SUB-002 | Subscription Flow | Cancel and Quota Stop | Cancel subscription and verify session creation eventually blocked | Active subscriber | 1. Cancel sub 2. Webhook fires 3. After grace period, attempt new session | Past grace period, POST /api/sessions returns 402 quota_exhausted | High | E2E
INT-SUB-003 | Subscription Flow | Pack Top-up | Buy session pack and confirm count increments | User with depleted quota | 1. Purchase pack 2. Webhook completes 3. Inspect quota | Quota increases by pack size; user can immediately start session | High | E2E
INT-SEC-001 | Security E2E | Cross-User Access | Verify user A cannot access user B's session | Two user accounts, B has session | 1. As user A, attempt GET /api/sessions/{B_session_id} 2. Attempt to join URL | 403 returned; join blocked | Critical | Security
INT-SEC-002 | Security E2E | No Public Discovery | Verify no API endpoint lists all active sessions publicly |  | 1. Probe likely endpoints (e.g. /api/sessions, /api/rooms) without auth | No endpoint returns session list; appropriate 401/403 | Critical | Security

## Non-Functional QA
Non-Functional QA — Test Cases
Status values: Not Started · In Progress · Pass · Fail · Blocked · Deferred
Test ID | Module | Feature | Test Scenario | Pre-conditions | Test Steps | Expected Result | Priority | Test Type | Status | Assigned Tester | Tested On | Browser / Device | Bug ID | Notes
NFR-PF-001 | Performance | Reading Room Load | Reading Room loads under 3s on broadband | Standard 50 Mbps connection | 1. Cold-load Reading Room URL 5 times 2. Measure load time | Average load <3s; 95th percentile <4s | Critical | Performance
NFR-PF-002 | Performance | Video Latency | End-to-end video latency under 150ms | Two devices on same network | 1. Visual hand-clap test 2. Use Livekit stats panel | Latency reading <150ms | Critical | Performance
NFR-PF-003 | Performance | Canvas Sync Latency | Annotation sync under 200ms | Active session | 1. Draw stroke 2. Time remote render | <200ms average across 50 strokes | Critical | Performance
NFR-PF-004 | Performance | Concurrent Sessions | Support 100 concurrent sessions at MVP | Load test environment | 1. Spin up 100 simulated sessions 2. Monitor server CPU/RAM and Livekit metrics | No service degradation; latency targets still met for sample sessions | High | Load
NFR-SE-001 | Security | JWT Forgery Resistance | Verify forged JWT rejected |  | 1. Sign JWT with wrong secret 2. Attempt protected call | 401 returned; signature validation fails | Critical | Security
NFR-SE-002 | Security | Invite Token Signing | Verify invite tokens are cryptographically signed |  | 1. Tamper with token payload 2. Attempt join | Tampered token rejected | Critical | Security
NFR-SE-003 | Security | Time-Limited Links | Verify session links expire as configured |  | 1. Create link with short TTL 2. Wait past TTL 3. Attempt to use | Link rejected with expiry error | High | Security
NFR-SE-004 | Security | No Chat Feature | Verify no in-session chat exists (per child safety design) |  | 1. Inspect UI in both Reading and Activity Rooms | No chat input or message panel anywhere in session UI | Critical | Security
NFR-SE-005 | Security | CORS | Verify CORS only allows approved origins |  | 1. Send cross-origin request from disallowed origin | CORS preflight blocks request | High | Security
NFR-SE-006 | Security | S3 Public Access | Verify S3 buckets are not publicly listable |  | 1. Anonymous GET on bucket root | Access denied; only signed URLs work | Critical | Security
NFR-AC-001 | Accessibility | Contrast Ratios | All brand color combinations meet WCAG AA (4.5:1) | Brand palette finalised | 1. Run axe DevTools or Lighthouse on key screens 2. Inspect contrast violations | No contrast violations on Reading Room, Activity Room, Lobby, Dashboard | High | Accessibility
NFR-AC-002 | Accessibility | Keyboard Navigation | Core flows usable by keyboard only |  | 1. Tab through lobby → join → session controls | Focus visible; all interactive elements reachable; no traps | Medium | Accessibility
NFR-AC-003 | Accessibility | Screen Reader Smoke | Basic screen reader smoke test | VoiceOver or NVDA | 1. Navigate dashboard and lobby 2. Inspect announcements | Major elements have meaningful labels; no nameless buttons | Medium | Accessibility
NFR-RL-001 | Reliability | Auto-Reconnect Time | Reconnect under 10s | See INT-RC-001 | 1. Drop network for 5s 2. Restore 3. Time to rejoin | <10s in 90% of trials | Critical | Reliability
NFR-RL-002 | Reliability | Sentry — Backend | Verify Sentry captures backend errors | Sentry configured | 1. Trigger a known exception in Django 2. Check Sentry dashboard | Issue appears in Sentry with stack trace within 1 min | High | Observability
NFR-RL-003 | Reliability | Sentry — Frontend | Verify Sentry captures frontend errors |  | 1. Trigger a known JS error 2. Check Sentry | Issue appears with source-mapped stack | High | Observability
NFR-CM-001 | Compliance | GDPR — Data Minimisation | Verify only necessary child data is stored |  | 1. Inspect DB schema and stored data | No PII of children beyond session metadata; no profile photos of minors stored | Critical | Compliance
NFR-CM-002 | Compliance | Data Deletion | Verify customer data can be deleted on request |  | 1. Submit deletion request through admin 2. Verify removal | User and session-linked PII removed; anonymised analytics retained per policy | High | Compliance
NFR-CM-003 | Compliance | Privacy Notice | Verify privacy notice present and accessible |  | 1. Inspect signup, lobby, marketing pages | Link to privacy policy visible; covers child data handling | High | Compliance

## Cross-Browser Matrix
Cross-Browser & Device Compatibility Matrix
Run the smoke suite (all Critical tests) on every supported browser/device. Mark Pass / Fail / N/A.
Smoke Test | Module | iOS Safari | iOS Chrome | Android Chrome | macOS Chrome | macOS Safari | Windows Chrome | Windows Edge | Windows Firefox | Notes
Join session via invite link | Auth & Invite
Both videos render | Reading Room
Two-way audio works | Reading Room
Host page turn syncs | Reading Room
Annotation pen draws and syncs | Reading Room
20-min timer visible & synced | Reading Room
Drawing activity loads & syncs | Activity Room
Drag-and-drop activity works | Activity Room
Quiz activity works | Activity Room
Hotspot activity (touch + mouse) | Activity Room
Lobby — camera/mic permissions | Lobby
Auto-reconnect after drop | Reliability
Customer dashboard renders | Dashboard
Admin login & book upload | Admin
Stripe checkout works | Billing

## Bug Log
Bug Log — Defect Tracker
Status values: Open · In Progress · Ready for Retest · Closed · Won't Fix · Deferred
Bug ID | Linked Test ID | Module | Title | Description | Steps to Reproduce | Severity | Priority | Status | Reported By | Assigned To | Resolution Notes
BUG-001 | FE-RR-008 | Reading Room | Page sync exceeds 500ms on slow 3G | Participant view consistently lags 600-900ms behind host on simulated 3G in Chrome DevTools. | 1. Throttle to slow 3G 2. Host turns page 5 times 3. Measure delta | High | High | Open | QA-Lead | Dev-1 | Sample row — replace with real bugs

## Priority Legend
Priority & Test Type Definitions
Priority
Priority | Definition | Beta Launch Gate
Critical | Blocks core platform value. Session cannot run, data corruption, security breach, or paywall failure. | Must be 100% Pass
High | Significantly degrades experience or violates a stated requirement. Workaround may exist. | Must be 100% Pass
Medium | Noticeable but non-blocking issue. Affects polish or non-core features. | 95% Pass acceptable
Low | Cosmetic or edge-case issues with minimal user impact. | Tracked, can ship with open issues
Test Type
Test Type | Definition | When to Run
Smoke | Quick sanity-check that core flows work at all. | Every build / deploy
Functional | Verify a feature behaves per its spec. | Per feature build + regression
UI | Layout, rendering, visual correctness. | Per feature build
API | Backend HTTP contract + payload validation. | Per backend change
Integration | Two or more components/services working together. | Per integration change
E2E | Full user journey across frontend + backend. | Pre-beta + nightly
Performance | Latency, throughput, load thresholds. | Pre-beta + per perf-relevant change
Security | Auth, authorisation, input validation, signing. | Pre-beta + per auth/security change
Reliability | Reconnection, retries, failure recovery. | Pre-beta + chaos test
Validation | Form/data validation rejects bad input. | Per form / API change
Audit | Verify logging and signal events fire. | Per signal/event change
Accessibility | WCAG compliance, keyboard, screen reader. | Pre-beta
Compliance | GDPR / data-handling requirements. | Pre-beta + per data-model change
Observability | Sentry / monitoring captures issues. | Pre-beta
Storage | S3 / file persistence behaviour. | Per storage change
Data | DB constraints, FKs, validation. | Per migration
Load | Concurrent user / session scaling. | Pre-beta